## Sheet1
Action Item # | Entry date | Original Due date | Planned date of completion | Actual date of completion | Assignee [ -> others to do the same] | Type | Section | Action | Status A=abandoned C=complete H=on hold P=partial | Disposition
28 | 2009-11-12 |  |  |  | Jerry Thrasher | NAP Binding |  | Jerry Thrasher will send a note to Mike Fenelon to find out if/how it is possible to handle multiple SHVs for the same environment, the same device class, and [possibly] the same SMI number (i.e., PWG)?
32 | 2009-12-10 |  |  |  | Joe Murdock | Market research |  | Joe Murdock will to develop a “Market Rationale” document – with help from within Sharp.
33 | 2009-12-10 |  |  |  | Randy Turner | SHV |  | Randy Turner will contact Symantec (when appropriate) to encourage discussion with the PWG about a SHV. | H | Blocked, waiting for AI #32 so we can send market rationale to Symantec.
34 | 2009-12-10 |  |  |  | Randy Turner | Remediation |  | Randy Turner will investigate Symantec’s products and their method(s) to “remediate noncompliant endpoints.” |  | will do a generic version
35 | 2009-12-10 |  |  |  | Joe Murdock | Remediation |  | Joe Murdock will investigate Microsoft’s method(s) of remediation. [Is it accomplished by passing a URL?] | P
36 | 2010-01-21 |  |  |  | Brian Smithson Joe Murdock | NAP Binding |  | In acknowledgements: change Dave Whitehead affiliation to “independent contractor” and Peter Cybuck to Kyocera Mita, and change Ron Bergman’s contact information to be consistent with what appears in IPP 2.0. Check to see if Kevin Sigl is still at HP.
37 | 2010-02-11 |  |  |  | Jerry Thrasher | Attributes |  | Same as AI #36 | C
38 | 2010-02-11 |  |  |  | Joe Murdock | Binding docs |  | Investigate localization issue
39 | 2010-02-11 | 2010-02-25 |  | 2010-02-12 | Joe Murdock | Remediation |  | post remediation document to whitepapers, add date stamp to filename | C
40 | 2010-02-11 | 2010-02-22 |  | 2010-02-22 | Brian Smithson Joe Murdock | agenda |  | add "how to implement remediation" to next meeting agenda | C
41 | 2010-02-25 |  |  |  | unassigned | Remediation |  | look at providing a remediation URL(s?)
42 | 2010-02-25 |  |  |  | Joe Murdock Jerry Thrasher Ira McDonald | Attributes |  | add a table of XML data type mapping for the semantic model and some brief normative text suggesting these items should be added to the MFD system object
43 | 2010-02-25 |  |  |  | Randy Turner | NEA Binding |  | Talk to Steve Hanna about recasting the NEA Binding document as a TCG TNC Binding document
COMPLETED ITEMS APPEAR BELOW:
30 | 2009-12-10 |  |  |  | Brian Smithson Joe Murdock | NAP Binding |  | Brian Smithson or Joe Murdock will clean up the NAP document, accepting the Dec 3 modifications, and will distribute an updated revision as Prototype status. | C
31 | 2009-12-10 |  |  |  | Brian Smithson Joe Murdock | NAP Binding |  | Brian Smithson or Joe Murdock will update the note in Appendix X in the NAP document to indicate that the PWG Secretary will “remove this Section.” | C
29 | 2009-12-10 |  |  |  | Joe Murdock | Market research |  | Joe Murdock will [edit and] post Peter Cybuck’s information about market research. | C | Due to proprietary concerns, specific information cannot be posted.
27 | 2009-10-15 |  |  | 2010-02-11 | Joe Murdock | NAP Binding |  | Joe Murdock will add NAP System Health ID to NAP Binding document and determine how to register a PWG system health ID value. | C | it uses the IANA value, so it is in effect already registered
26 | 2009-10-15 |  |  |  | Joe Murdock | SCCM |  | Joe Murdock will follow up with Eran Dvir (Microsoft) about the SCCM issues, questions, and capabilities. [Ref: AI #22] | A
25 | 2009-09-17 |  |  |  | Peter Cybuck | Market research |  | Peter Cybuck will do some market research about whether customers will accept the proposed method of gaining network access via SCCM. | C | Yes, large but unspecified companies are interested.
24 | 2009-08-18 |  |  | 2009-10-15 | Randy Turner | NEA Binding |  | Randy Turner will ask the NEA e-mail list about their assumptions on modeling [sub-]components with regard to MFD subunits. (Why does NEA not address BIOS and/or NICs as components within a PC?) | C | Randy has received two responses. Steve Hanna (NEA Chair) is working on a list of comments on the NEA binding document.
23 | 2009-08-18 |  |  |  | Mike Fenelon | Value Proposition |  | Mike Fenelon will take on the responsibility for creating a “value proposition” document to help justify the reason behind HCD NAP development. Peter Cybuck and Ron Nevo will provide market information as possible. | A | Jane Maliouta has transferred groups and will no longer work on this task. Mike is attempting to find the right person within Microsoft to do the actual work. (subsumed by AI #32)
22 | 2009-08-18 |  |  | 2009-10-15 | Joe Murdock | NAP Binding |  | Joe Murdock will examine the possible mapping of HCD attributes to SCCM and evaluate the resulting “HCD health assessment” benefit. [This should also result in a list of deficiencies and recommended extensions to be suggested to the MS NAP team.] | C | Proposed mapping spreadsheet was distributed. Questions have been sent to Microsoft.
21 | 2009-08-06 |  |  | 2009-08-18 | Joe Murdock | NAP Binding |  | Joe Murdock will update the NAP Binding specification to address the comments from the June face-to-face meeting and post for review. | C
20 | 2009-07-09 |  |  | 2009-09-17 | Randy Turner |  |  | Randy Turner will post a link to the RSA discussion of TPM alternatives. | C
19 | 2009-06-23 |  |  | 2009-08-18 | Ron Nevo |  |  | Ron Nevo will collect all questions for the Microsoft NAP team that are submitted to the IDS reflector and will pass them along to Microsoft. | C
18 | 2009-06-23 |  |  | 2009-08-06 | Brian Smithson, Joe Murdock | NAP Binding |  | Brian Smithson and/or Joe Murdock will include the attributes that were added to the latest Attribute specification in the next version of the NAP Binding document. | C
17 | 2009-06-23 |  |  | 2009-08-18 | Joe Murdock |  |  | Joe Murdock will send an e-mail to one of the NAP team members asking his opinion on the use of an opaque value for HCD Certification State—and specifically the topic of using vendor-specific plug-ins. | C
16 | 2009-06-04 |  |  | 2009-06-18 | Jerry Thrasher | F2F |  | Jerry Thrasher will add the topic of including IDS information in the MFD Semantic Model to the June Plenary meeting. | C
15 | 2009-06-04 |  |  | 2009-06-23 | Jerry Thrasher | Attributes |  | Jerry Thrasher will create yet another draft of the Attribute document to include corrections identified at the June 4 teleconference. | C
14 | 2009-05-21 |  |  | 2009-06-04 | Brian Smithson | TCG |  | Brian Smithson will communicate the results of the straw poll to the TCG board member responsible for the TCG HCWG. | C
13 | 2009-04-29 |  |  | 2009-05-21 | Dave Whitehead | Telecon |  | Dave Whitehead will announce the next teleconference. | C
12 | 2009-04-29 |  |  | 2009-07-20 | Mike Fenelon | NAP |  | Mike Fenelon will coordinate the next opportunity for a discussion with the Microsoft NAP team. | C
11 | 2009-04-29 |  |  | 2009-05-21 | Dave Whitehead | NEA |  | Dave Whitehead will send a note to Steve Hanna providing the details of the group’s resolutions to his comments. | C
10 | 2009-04-16 |  |  | 2009-11-12 | Brian Smithson | TCG |  | Brian Smithson will investigate whether a formal relationship document can be created between TCG and PWG. He will find out their position on liaison agreements. | C | TCG Board says we can continue with the existing informal relationship. It will be similar to the relationship held with the IEEE P2600 group. [Status information, but no document access.]
9 | 2009-04-16 |  |  | 2009-04-29 | All | TCG |  | Everyone will review Steve Hanna’s comments [http://www.pwg.org/hypermail/ids/0242.html] and be prepared for discussion at the next face-to-face meeting. | C
8 | 2009-03-26 |  |  | 2009-05-21 | Ron Nevo, Dave Whitehead | Action items |  | Ron and Dave will maintain an Action Item spreadsheet that assigns unique IDs to each Action Item and retains the resolution history. | C
7 | 2009-03-26 |  |  | 2009-05-21 | Dave Whitehead | Attributes Microsoft |  | Dave Whitehead and Randy Turner will compile a set of questions that are intended for Microsoft—and maintain the answers on an ongoing basis for future reference. This list should include the topic of the four SOH attributes: MS-Quarantine-State MS-Machine-Inventory MS-Packet-Info MS-CorrelationId | C
6 | 2009-03-26 |  |  | 2009-03-26 | Randy Turner | NEA |  | Randy Turner will send a link to the updated Attributes document to the NEA WG, and solicit their comments. | C
5 | 2009-03-26 |  |  | 2009-04-16 | Dave Whitehead | NAP |  | Dave Whitehead will attempt to resolve the following issue: Which of the defined transport(s) are required to be supported in order to guarantee a device can attach to the network? MS defines DHCP, 802.1x, IPSec, and VPN and has extended each to add SOH information. So, in an environment where we are attaching wirelessly via 802.1x and receive our IP address from DHCP, what happens if we only support SOH over DHCP (or 802.1x)? Will we attach or fail? | C | This issue has been added to the list of questions to be discussed with the MS NAP team.
4 | 2009-03-26 |  |  | 2009-05-21 | Dave Whitehead | NAP Microsoft |  | Dave Whitehead will coordinate with Randy Turner to generate a proposal to Microsoft on proceeding with obtaining NAP information on what they envision would be the content of a profile—including remediation. Need to identify the appropriate point of contact within Microsoft. | C
3 | 2009-03-26 |  |  | 2009-04-29 | Joe Murdock | NAP |  | Joe Murdock will include sequence diagrams as illustrative examples for the NAP binding document. | C
2 | 2009-04-28 |  | 2009-06-23 | 2009-06-23 | Joe Murdock | NAP |  | Joe Murdock will add NAP protocol information to document and update the conformance section. | C
1 | 2009-04-28 |  |  | 2009-12-03 | Randy Turner | NEA |  | Randy Turner will try to find other contacts that would be willing to work with the PWG to help deploy NEA health assessment. (Juniper, Symantec, Cisco are suggested candidates.) Is someone willing to sit down with the PWG and “have discussions”? | C | Randy says he has spoken to several of these companies, and based on a recent document posting [ftp://ftp.pwg.org/pub/pwg/ids/white/ids-ai.pdf], he feels that this Action Item can be closed. He said that no specific “back door” relationships with any of the companies are necessary. The products that we could work with are already generally available today.
x