## Sheet1
Action Item # | Entry date | Original Due date | Planned date of completion | Actual date of completion | Assignee [ -> others to do the same] | Type | Section | Action | Status A=abandoned C=complete H=on hold P=partial | Disposition
33 | 2009-12-10 |  |  |  | Randy Turner | SHV |  | Randy Turner will contact Symantec (when appropriate) to encourage discussion with the PWG about a SHV. |  | No longer blocked waiting for AI #32 so we can send market rationale to Symantec.
34 | 2009-12-10 |  |  |  | Randy Turner | Remediation |  | Randy Turner will investigate Symantec’s products and their method(s) to “remediate noncompliant endpoints.” |  | Symantec wants an NDA, but PWG cannot do an NDA; will do a generic version; should we invite Symantec to a PWG IDS teleconference?
44 | 2010-03-11 |  |  |  | Jerry Thrasher Ira McDonald Brian Smithson | NEA Binding |  | Recast the NEA Binding document as a TCG TNC Binding document |  | Make it a TCG document, not an IETF NEA document
53 | 2010-05-20 | 2010-06-10 |  |  | Joe Murdock |  |  | Write an MPSA newsletter article for publication in November |  | Joe will work with Bill on articles, surveys, etc., to create and maintain a presence with MPSA. Planning to have something to review at the next F2F.
58 | 2010-06-11 | 2010-08-03 |  |  | Joe Murdock and Ira McDonald | SCCM |  | Create a first draft SCCM binding spec based on the NAP binding spec | H | MS is releasing R3 of SCCM and also a beta of "R-next", while at the same time adding power management; WIMS group may also be interested. On hold due to priorities.
60 | 2010-06-11 |  |  |  | Joe Murdock | auth |  | First draft of potential resource predicate values (objects, operations, etc.) | P
63 | 2010-08-06 |  |  |  | Bill Wagner | MPSA |  | Add the plan to a new section of the PWG wiki | P | Intro completed but no plan yet and not yet linked to the main page
64 | 2010-09-30 |  |  |  | Joe Murdock |  |  | Outline an overview of IA&A |  | review at F2F
65 | 2010-10-20 |  |  |  | Joe Murdock Brian Smithson | admin |  | Update the PWG-IDS Charter
66 | 2010-10-20 |  |  |  | Brian Smithson Joe Murdock Ira McDonald | admin |  | Create a project charter for creating IEEE 2600.1 Supporting Documents
COMPLETED ITEMS APPEAR BELOW:
62 | 2010-08-06 |  |  | 2010-09-29 | Joe Murdock | ATR |  | Add Natural Language to the conformance list in HCD-ATR section 6 | C
61 | 2010-08-06 |  |  | 2010-09-29 | Joe Murdock | ATR and NAP |  | Change the firmware patches list order from reverse to normal in both HCD-ATR and HCD-NAP | C
59 | 2010-06-11 | 2010-08-03 |  | 2010-08-03 | Michael Sweet | log format |  | Create a first draft of a common logging specification | C
57 | 2010-06-11 |  |  |  | Joe Murdock | ATR and NAP |  | Patch attributes should be array of patches in order they are applied | C
56 | 2010-06-11 |  |  |  | Pete Zehler Ira | Schema |  | Make simple element xxxPatches as a complex type sequence 0~n xxxPatch | C
55 | 2010-06-11 | 2010-08-03 |  |  | Joe Murdock | ATR |  | Add language attribute to ATR | C
54 | 2010-06-11 | 2010-08-03 |  |  | Joe Murdock | NAP |  | Make language attribute required | C
52 | 2010-05-20 | 2010-06-10 | 2010-06-11 |  | all | log format |  | Look at LogFS (http://www.logfs.org) and syslog (http://datatracker.ietf.org/wg/syslog/ and optionally http://www.syslog.org/) | C | we will follow syslog
51 | 2010-04-08 |  |  | 2010-06-05 | Randy Turner | log format |  | compile wishlist for standard log content and format | C
50 | 2010-04-08 | 2010-04-22 |  | 2010-05-18 | Brian Smithson | log format |  | summarize current log standards for 2600.1 | C | posted to ftp ids/white
49 | 2010-04-08 | 2010-04-22 | 2010-06-11 | 2010-06-11 | all | auth |  | look at XACML and geoXACML (www.geoxacml.org) | C
48 | 2010-04-08 | 2010-04-22 |  | 2010-06-09 | Randy Turner | auth |  | post to the IDS list the problem statement about authorization | C
47 | 2010-04-08 | 2010-04-22 | 2010-06-11 |  | all | general |  | Take another look at SCAP and figure out what if anything to do in IDS | A | consider re-opening in Q3 2010
46 | 2010-04-08 | 2010-04-22 |  | 2010-04-22 | Joe Murdock | all docs |  | Change document titles (and page headers, and references to the documents) according to PWG decision to use the acronym and not the entire name “Printer Working Group”. | C | not the NEA doc, since it is going away
45 | 2010-04-08 |  |  |  | Ira McDonald Pete Zehler | Attributes |  | Add HCD attributes to the system object in the MFD semantic model | C
43 | 2010-02-25 |  |  | 2010-03-11 | Randy Turner | NEA Binding |  | Talk to Steve Hanna about recasting the NEA Binding document as a TCG TNC Binding document | C | Steve said yes
42 | 2010-02-25 |  |  | 2010-04-08 | Joe Murdock Jerry Thrasher Ira McDonald | Attributes |  | add a table of XML data type mapping for the semantic model and some brief normative text suggesting these items should be added to the MFD system object | C
41 | 2010-02-25 |  | 2010-08-03 | 2010-07-30 | Joe Murdock | Remediation |  | look at providing a remediation specification | C | Joe has begun making an actual spec for remediation based on whitepaper
40 | 2010-02-11 | 2010-02-22 |  | 2010-02-22 | Brian Smithson Joe Murdock | agenda |  | add "how to implement remediation" to next meeting agenda | C
39 | 2010-02-11 | 2010-02-25 |  | 2010-02-12 | Joe Murdock | Remediation |  | post remediation document to whitepapers, add date stamp to filename | C
38 | 2010-02-11 |  | 2010-06-10 | 2010-06-07 | Joe Murdock | Binding docs |  | Investigate localization issue | C | Cannot find any information about this in MS documents; Joe will add a localization attribute to the NAP binding spec
37 | 2010-02-11 |  |  |  | Jerry Thrasher | Attributes |  | Same as AI #36 | C
36 | 2010-01-21 |  |  | 2010-03-10 | Brian Smithson Joe Murdock | NAP Binding |  | In acknowledgments: change Dave Whitehead affiliation to “independent contractor” and Peter Cybuck to Kyocera Mita, and change Ron Bergman’s contact information to be consistent with what appears in IPP 2.0. Check to see if Kevin Sigl is still at HP. | C | according to his linkedin page, Kevin is still at HP
35 | 2009-12-10 |  |  | 2010-04-22 | Joe Murdock | Remediation |  | Joe Murdock will investigate Microsoft’s method(s) of remediation. [Is it accomplished by passing a URL?] | C | Yes it is
32 | 2009-12-10 |  | 2010-04-22 | 2010-04-22 | Joe Murdock | Market research |  | Joe Murdock will to develop a “Market Rationale” document – with help from within Sharp. | C | first draft published; update and post for discussion on 4/22/10
31 | 2009-12-10 |  |  |  | Brian Smithson Joe Murdock | NAP Binding |  | Brian Smithson or Joe Murdock will update the note in Appendix X in the NAP document to indicate that the PWG Secretary will “remove this Section.” | C
30 | 2009-12-10 |  |  |  | Brian Smithson Joe Murdock | NAP Binding |  | Brian Smithson or Joe Murdock will clean up the NAP document, accepting the Dec 3 modifications, and will distribute an updated revision as Prototype status. | C
29 | 2009-12-10 |  |  |  | Joe Murdock | Market research |  | Joe Murdock will [edit and] post Peter Cybuck’s information about market research. | C | Due to proprietary concerns, specific information cannot be posted.
28 | 2009-11-12 |  |  | 2010-04-08 | Jerry Thrasher | NAP Binding |  | Jerry Thrasher will send a note to Mike Fenelon to find out if/how it is possible to handle multiple SHVs for the same environment, the same device class, and [possibly] the same SMI number (i.e., PWG)? | A | No response from anyone at Microsoft since at least November.
27 | 2009-10-15 |  |  | 2010-02-11 | Joe Murdock | NAP Binding |  | Joe Murdock will add NAP System Health ID to NAP Binding document and determine how to register a PWG system health ID value. | C | it uses the IANA value, so it is in effect already registered
26 | 2009-10-15 |  |  |  | Joe Murdock | SCCM |  | Joe Murdock will follow up with Eran Dvir (Microsoft) about the SCCM issues, questions, and capabilities. [Ref: AI #22] | A
25 | 2009-09-17 |  |  |  | Peter Cybuck | Market research |  | Peter Cybuck will do some market research about whether customers will accept the proposed method of gaining network access via SCCM. | C | Yes, large but unspecified companies are interested.
24 | 2009-08-18 |  |  | 2009-10-15 | Randy Turner | NEA Binding |  | Randy Turner will ask the NEA e-mail list about their assumptions on modeling [sub-]components with regard to MFD subunits. (Why does NEA not address BIOS and/or NICs as components within a PC?) | C | Randy has received two responses. Steve Hanna (NEA Chair) is working on a list of comments on the NEA binding document.
23 | 2009-08-18 |  |  |  | Mike Fenelon | Value Proposition |  | Mike Fenelon will take on the responsibility for creating a “value proposition” document to help justify the reason behind HCD NAP development. Peter Cybuck and Ron Nevo will provide market information as possible. | A | Jane Maliouta has transferred groups and will no longer work on this task. Mike is attempting to find the right person within Microsoft to do the actual work. (subsumed by AI #32)
22 | 2009-08-18 |  |  | 2009-10-15 | Joe Murdock | NAP Binding |  | Joe Murdock will examine the possible mapping of HCD attributes to SCCM and evaluate the resulting “HCD health assessment” benefit. [This should also result in a list of deficiencies and recommended extensions to be suggested to the MS NAP team.] | C | Proposed mapping spreadsheet was distributed. Questions have been sent to Microsoft.
21 | 2009-08-06 |  |  | 2009-08-18 | Joe Murdock | NAP Binding |  | Joe Murdock will update the NAP Binding specification to address the comments from the June face-to-face meeting and post for review. | C
20 | 2009-07-09 |  |  | 2009-09-17 | Randy Turner |  |  | Randy Turner will post a link to the RSA discussion of TPM alternatives. | C
19 | 2009-06-23 |  |  | 2009-08-18 | Ron Nevo |  |  | Ron Nevo will collect all questions for the Microsoft NAP team that are submitted to the IDS reflector and will pass them along to Microsoft. | C
18 | 2009-06-23 |  |  | 2009-08-06 | Brian Smithson, Joe Murdock | NAP Binding |  | Brian Smithson and/or Joe Murdock will include the attributes that were added to the latest Attribute specification in the next version of the NAP Binding document. | C
17 | 2009-06-23 |  |  | 2009-08-18 | Joe Murdock |  |  | Joe Murdock will send an e-mail to one of the NAP team members asking his opinion on the use of an opaque value for HCD Certification State—and specifically the topic of using vendor-specific plug-ins. | C
16 | 2009-06-04 |  |  | 2009-06-18 | Jerry Thrasher | F2F |  | Jerry Thrasher will add the topic of including IDS information in the MFD Semantic Model to the June Plenary meeting. | C
15 | 2009-06-04 |  |  | 2009-06-23 | Jerry Thrasher | Attributes |  | Jerry Thrasher will create yet another draft of the Attribute document to include corrections identified at the June 4 teleconference. | C
14 | 2009-05-21 |  |  | 2009-06-04 | Brian Smithson | TCG |  | Brian Smithson will communicate the results of the straw poll to the TCG board member responsible for the TCG HCWG. | C
13 | 2009-04-29 |  |  | 2009-05-21 | Dave Whitehead | Telecon |  | Dave Whitehead will announce the next teleconference. | C
12 | 2009-04-29 |  |  | 2009-07-20 | Mike Fenelon | NAP |  | Mike Fenelon will coordinate the next opportunity for a discussion with the Microsoft NAP team. | C
11 | 2009-04-29 |  |  | 2009-05-21 | Dave Whitehead | NEA |  | Dave Whitehead will send a note to Steve Hanna providing the details of the group’s resolutions to his comments. | C
10 | 2009-04-16 |  |  | 2009-11-12 | Brian Smithson | TCG |  | Brian Smithson will investigate whether a formal relationship document can be created between TCG and PWG. He will find out their position on liaison agreements. | C | TCG Board says we can continue with the existing informal relationship. It will be similar to the relationship held with the IEEE P2600 group. [Status information, but no document access.]
9 | 2009-04-16 |  |  | 2009-04-29 | All | TCG |  | Everyone will review Steve Hanna’s comments [http://www.pwg.org/hypermail/ids/0242.html] and be prepared for discussion at the next face-to-face meeting. | C
8 | 2009-03-26 |  |  | 2009-05-21 | Ron Nevo, Dave Whitehead | Action items |  | Ron and Dave will maintain an Action Item spreadsheet that assigns unique IDs to each Action Item and retains the resolution history. | C
7 | 2009-03-26 |  |  | 2009-05-21 | Dave Whitehead | Attributes Microsoft |  | Dave Whitehead and Randy Turner will compile a set of questions that are intended for Microsoft—and maintain the answers on an ongoing basis for future reference. This list should include the topic of the four SOH attributes: MS-Quarantine-State MS-Machine-Inventory MS-Packet-Info MS-CorrelationId | C
6 | 2009-03-26 |  |  | 2009-03-26 | Randy Turner | NEA |  | Randy Turner will send a link to the updated Attributes document to the NEA WG, and solicit their comments. | C
5 | 2009-03-26 |  |  | 2009-04-16 | Dave Whitehead | NAP |  | Dave Whitehead will attempt to resolve the following issue: Which of the defined transport(s) are required to be supported in order to guarantee a device can attach to the network? MS defines DHCP, 802.1x, IPSec, and VPN and has extended each to add SOH information. So, in an environment where we are attaching wirelessly via 802.1x and receive our IP address from DHCP, what happens if we only support SOH over DHCP (or 802.1x)? Will we attach or fail? | C | This issue has been added to the list of questions to be discussed with the MS NAP team.
4 | 2009-03-26 |  |  | 2009-05-21 | Dave Whitehead | NAP Microsoft |  | Dave Whitehead will coordinate with Randy Turner to generate a proposal to Microsoft on proceeding with obtaining NAP information on what they envision would be the content of a profile—including remediation. Need to identify the appropriate point of contact within Microsoft. | C
3 | 2009-03-26 |  |  | 2009-04-29 | Joe Murdock | NAP |  | Joe Murdock will include sequence diagrams as illustrative examples for the NAP binding document. | C
2 | 2009-04-28 |  | 2009-06-23 | 2009-06-23 | Joe Murdock | NAP |  | Joe Murdock will add NAP protocol information to document and update the conformance section. | C
1 | 2009-04-28 |  |  | 2009-12-03 | Randy Turner | NEA |  | Randy Turner will try to find other contacts that would be willing to work with the PWG to help deploy NEA health assessment. (Juniper, Symantec, Cisco are suggested candidates.) Is someone willing to sit down with the PWG and “have discussions”? | C | Randy says he has spoken to several of these companies, and based on a recent document posting [ftp://ftp.pwg.org/pub/pwg/ids/white/ids-ai.pdf], he feels that this Action Item can be closed. He said that no specific “back door” relationships with any of the companies are necessary. The products that we could work with are already generally available today.
x